Zendesk Co-Pilot

Phasing & Cost-Optimised Plan

How we ship end-to-end with Claude API as the only ongoing cost

Prepared for: Subhajit Das · BetterPlace

Date: 30 April 2026

Version: 0.1

# 1. The cost constraint, in plain language

You said: "I want to spend only on Claude API cost and nothing else if possible apart from my already ZD license. Plan and optimise accordingly. If we need to host on a server absolutely let me know."

Short answer: yes, this is achievable. Every piece of software in the stack — database, vector search, web framework, sync workers, AI workers, tunnel, auth — has a free/open-source choice that handles your volume comfortably. The only ongoing cost driver is Claude API calls. Estimated $150–400/month at your ticket volume, optimisable downward.

There is one infrastructure question that does need a decision: where the always-on Linux box lives. Three options below; the cheapest is $0/month (use a machine you already have).

# 2. The cost-zero stack

Every layer of the system uses open-source / free-tier software. None of these have a license fee or usage cost at your volume.

| Layer | Choice | Cost |
| --- | --- | --- |
| Database | SQLite with sqlite-vec extension (vector search built in) | $0 forever |
| Web framework | FastAPI + HTMX (Python), server-rendered, low-JS | $0 |
| Sync worker | Python — httpx, tenacity, schedule | $0 |
| AI worker | Python — official anthropic SDK | $0 |
| Auth | Google Workspace SSO via OAuth (you already have Workspace) | $0 |
| Tunnel / remote access | Cloudflare Tunnel (free tier) or Tailscale (free up to 100 devices) | $0 |
| Backups | Daily SQLite snapshot to a NAS or external drive | $0 |
| Process manager | systemd or launchd (built into the OS) | $0 |
| Container orchestration | docker-compose (one config file, no Kubernetes) | $0 |

Notes on why these choices fit the cost constraint:

- SQLite over Postgres: at <= 1k tickets/day, SQLite is faster than Postgres and needs no server. sqlite-vec gives you vector similarity search inside the same DB — no separate vector store.

- FastAPI + HTMX over React: a single Python process serves the UI. No build pipeline, no Node, no CDN. Pages render server-side and feel snappy.

- Cloudflare Tunnel over a public IP: creates a stable HTTPS URL that points at your local machine. No ports opened, no firewall changes, no public IP needed. Free tier covers your volume by orders of magnitude.

- Google SSO over building auth: you already have Workspace. Each engineer logs in with their @betterplace.co.in account. No password DB to manage.

# 3. The Claude API cost — how we keep it low

At ~1,000 tickets/day (the upper bound of your range), naive per-ticket Claude calls cost roughly $300–400/month on Sonnet. With the optimisations below we expect $150–250/month for production use; the same techniques cap unexpected spikes.

## 3.1 Optimisations baked into Phase 1

- Skip re-analysis on quiescent tickets. A ticket gets re-run only when its conversation has actually changed. Solved tickets that no-one touches don't cost anything.

- Hard monthly budget cap. Set in code. When usage approaches it the AI worker pauses and emails you. No surprise bills.

- Embeddings computed once. When the conversation extends, only the new comments are re-embedded.

- JSON-mode strict outputs. Claude returns a tight schema; no wasted tokens on chatty natural-language responses.

## 3.2 Optimisations available in Phase 2+

- Route easy tickets to Haiku. Short, well-formed Operations Tasks (e.g. agreement-copy requests) go to Haiku at ~10x lower cost; only ambiguous or complex tickets escalate to Sonnet. Roughly cuts cost 50–60%.

- Prompt caching. Anthropic caches the long system prompt (your field taxonomy is ~3k tokens of stable context). Caching cuts input cost ~80% on the cached portion. Net: another ~25% reduction on average.

- Batch nightly re-runs. Solved tickets get one re-analysis at end of day in a batch (cheaper than per-ticket calls) to take advantage of any model improvements.

## 3.3 Cost ceiling vs. value

At your ticket volume the worst-case Claude bill is ~$400/month. For comparison, eliminating one hour of agent re-tagging and resolution-writing per day at typical cost is more than that. The system pays for itself almost immediately on the field-correction workflow alone, before any KB or write-back features are turned on.

# 4. The infrastructure decision: where the always-on box lives

Everything else is free. The one decision that has cost implications is what hardware runs the system 24/7.

| Option | Up-front | Ongoing | Trade-offs |
| --- | --- | --- | --- |
| A. Use an existing always-on machine in your office (RECOMMENDED if available) | $0 | $0 | Best fit. If you have any spare desktop, NAS, or always-on workstation — even an older Mac — it can run this. Needs ~16 GB RAM and Docker. |
| B. Buy a Mac mini M2 (or NUC equivalent) | ~$700 | $0 | One-time hardware spend. Sits in the office, sleep disabled. Effectively zero cost over time. Best if no spare machine exists. |
| C. Run on Subhajit's laptop temporarily | $0 | $0 | Works for the proof-of-value phase but team access drops every time you close the lid. Acceptable for Phase 1 testing only. |
| D. Small VPS (Hetzner, Contabo) | $0 | ~$5–10 / month | Predictable but breaks the "Claude API only" constraint. Recommended only if you have no spare hardware AND need true 24/7 access. |

Recommendation: start on Option C (your laptop) for the first build week, then move to Option A if you have a spare machine, otherwise Option B. The Mac mini purchase pays for itself in roughly 2 months versus a VPS at typical ICP pricing, and is yours to keep.

# 5. Phases — what we ship, in what order

Each phase is independently shippable. After Phase 1 the system is delivering value; everything after is incremental. You can pause between phases at no risk.

| Phase | Duration | What ships | Net new cost |
| --- | --- | --- | --- |
| 0 | DONE | Design + 10-ticket proof + agent-view mockup + repository seed | $0 (we are here) |
| 1 — Local MVP | ~2 weeks | Sync worker, AI worker, agent dashboard live, single-host deploy with tunnel. Read-only. | Claude API only ($150–250/mo) |
| 2 — Confluence + Jira + KB | ~2–3 weeks | Confluence indexing + auto-link, Jira ID auto-detect, KB article auto-draft → review → publish. | Claude API only (slight increase from embedding new pages) |
| 3 — Suggested replies + write-back | ~2 weeks | AI evaluates every agent reply; drafts improved version when reply is incomplete. "Apply correction" writes back to ZD. Auto-rules (recall merge, backfill on merge, Reliance bucketization required). | Claude API only |
| 4 — Leadership dashboard | ~1–2 weeks | Separate URL, customer health scorecards, agent quality metrics, emerging-bucket alerts, weekly exec digest. | Claude API only |
| 5 — Continuous polish | ongoing | Add new groups, customer-specific rules, accuracy tuning, cost tuning. | Claude API only |

## 5.1 Phase 1 deliverables in detail

- Sync worker pulls from Zendesk every 5 minutes, writes to local SQLite.

- AI worker calls Claude on every new/updated ticket, writes structured insights into the same DB.

- Web app renders the agent view (same shape as the mockup we already built).

- SLA pickup banner appears automatically when a ticket meets the rule (status ∈ new/open + no agent comment + no assignee + age > 4h).

- Repository auto-grows: every solved ticket adds an entry that future tickets can find.

- Cloudflare Tunnel exposes the dashboard at a stable URL like https://copilot.betterplace.co.in.

- Read-only first — agents see suggestions but click through to Zendesk to apply them. This is deliberate so you build trust before write-back goes live in Phase 3.

## 5.2 Phase 2 deliverables in detail

- Confluence index: weekly job that pulls every page from your chosen spaces and embeds them into the same vector store as tickets. Suggestions cite page title + URL.

- Jira auto-detect: regex on conversation text catches Jira IDs (e.g. SMS-1124) and pre-fills the Jira ID field with one-click confirmation.

- KB auto-draft: when a solved ticket is marked KB-worthy, AI drafts a Confluence page in markdown (sample already created at data/kb_drafts/593795_color_code_format.md). Drafts queue for review; one-click "Publish" via Atlassian API uploads to your chosen space.

- Existing-page suggestion: on a new ticket, the top-matching Confluence page surfaces in the AI panel and pre-fills the KB Article field.

## 5.3 Phase 3 deliverables in detail

- Suggested-reply engine: AI evaluates each agent reply against the ticket type. Failure modes covered: (a) Issue ticket with root cause not stated, (b) Task ticket with action not described, (c) Training ticket with steps not provided. Live demo for #593721 and #593760 already in the agent view report.

- "Apply correction" writes back to Zendesk via /api/v2/tickets/{id}.json with full audit log of who applied what and when.

- Auto-rules: Outlook recall merge, Reliance Bucketization required (block closure when empty), backfill custom fields on merge.

- Approval threshold configurable: e.g. "auto-apply field corrections at >= 95% confidence; surface 80–95% to agent for one-click approval; suppress < 80%."

## 5.4 Phase 4 deliverables in detail

- Separate Leadership URL (e.g. /leadership) with role-based access — only managers see it.

- Customer health scorecards: tickets per customer per week, time-to-resolve trend, escalation rate, SLA breach count.

- Agent quality metrics: field-tagging accuracy, KB-link rate, "How resolved?" completeness score, suggested-reply acceptance rate.

- Emerging-bucket detection: cluster of similar tickets in 24h that don't map to existing categories — early warning for new failure modes.

- Weekly exec digest: auto-generated email or Slack message with the top 3 trends, the top 3 customer pain points, the top 3 KB-article gaps.

# 6. Suggested-reply engine — how it works

Triggered after the agent writes a reply but before they hit send. Adds 2–4 seconds latency for the AI evaluation; can be skipped per-agent if not wanted.

## 6.1 Reply-evaluation prompt (sketch)

The AI gets: the ticket type (Issue / Task / Training), the conversation so far, and the agent's draft reply. It outputs a JSON object: {complete: bool, missing: [list of named gaps], suggested_reply: text, reasoning: text}.

## 6.2 Failure modes covered

| Ticket type | What gets flagged |
| --- | --- |
| Issue | Reply doesn't state the root cause; doesn't reassure on recurrence; doesn't set expectations on follow-up. |
| Task | Reply doesn't name the action taken; doesn't reference the entity (driver code, profile ID, ticket ID); doesn't confirm verifiable side-effects (e.g. push notification dispatched). |
| Training | Reply doesn't walk through the steps; doesn't link to the relevant Confluence runbook; doesn't confirm the user has access to the feature being explained. |

## 6.3 Live examples in the agent view report

- #593721 — Task ticket. Original reply: "Vendor has been updated." AI flags: doesn't name what was done, doesn't reference the driver code, doesn't confirm the push notification. Suggested reply incorporates all three.

- #593760 — Issue ticket. Original reply mentions the cause (yesterday's lag) but as an aside. AI flags: customer might miss it, no reassurance on recurrence. Suggested reply leads with the root cause as a clearly-labelled section.

# 7. Confluence integration — how it works end-to-end

## 7.1 Direction A: suggest existing pages on new tickets

- Weekly job pulls every Confluence page from the spaces you nominate (e.g. PS, OPS).

- Each page is chunked, embedded with the same model used for tickets, and stored in the vector index alongside ticket embeddings.

- When a new ticket arrives, the AI worker embeds the conversation and runs vector similarity against all indexed Confluence pages.

- Top match (above a similarity threshold) is surfaced in the agent panel with a citation, an excerpt, and a one-click "Attach to KB Article field" action.

## 7.2 Direction B: auto-draft new pages from KB-worthy resolutions

- When a ticket is solved, the AI worker scores it for "KB-worthiness" — recurring failure mode + no existing matching Confluence page + clear resolution steps in the conversation.

- Above the threshold, AI drafts a full markdown page: problem statement, symptoms, root cause, resolution steps, verification checklist, "next time" guidance.

- Draft saved to data/kb_drafts/<ticket_id>_<topic>.md. Sample already created for #593795 — open it to see the shape.

- Drafts queue in the dashboard for human review. Reviewer can edit in-line, then click "Publish to Confluence". Publish uses Atlassian REST API to create the page in the configured space + parent page.

- Once published, the new page is indexed (Direction A) and immediately available to suggest on similar future tickets.

## 7.3 What this means for the "agents skip KB Article" problem you flagged

In your data, 9 of 10 tickets had KB Article empty or "NA". The two-direction system flips this: existing pages are pre-suggested (no agent typing required) and new pages are auto-drafted (agent reviews instead of writes). Net effect: KB hygiene becomes the AI's job, not the agent's; the agent's job is just to approve.

# 8. Risks and how we mitigate them

| Risk | Mitigation |
| --- | --- |
| Claude API cost runs higher than estimated. | Hard monthly cap in code; alerts at 50% / 75% / 100%. Worst-case the worker pauses, not your bank account. |
| Agents distrust AI suggestions and ignore them. | Read-only Phase 1 builds trust before any write-back. Confidence rings on every suggestion let agents calibrate themselves. The 10-ticket proof gives senior agents (Eshwaran, Wrishov) the chance to validate before rollout. |
| Your Mac/laptop offline = team locked out. | Choose Option A or B from the hosting table; not Option C long-term. Cloudflare Tunnel can route to a backup machine if you set one up. |
| Zendesk API rate limits. | Sync worker uses incremental exports + exponential backoff. Worst-case impact is delayed sync, not data loss. |
| Reliance custom rules change. | Bucketization-required and Customer Name dropdown updates are config, not code. You add new options without a developer. |
| Sensitive ticket data sent to Anthropic. | Anthropic API does not train on data sent via the API. We can also redact PII (phone, exact addresses) before the prompt is sent — this is a checkbox in the AI worker config. |

# 9. Decision points needed from you

- Hosting option (A / B / C / D from §4). Best to confirm before Phase 1 starts so the deploy step matches the chosen target. If unsure, Option B (Mac mini) is the safe long-term pick.

- Cloudflare vs Tailscale tunnel. Cloudflare gives a stable public URL like copilot.betterplace.co.in. Tailscale gives zero-config private network access (team installs the Tailscale app). Either works.

- Auth method. Google Workspace SSO recommended if you use Workspace. Magic-link email is the alternative.

- Confluence spaces to index. Need the space keys (e.g. PS, OPS) and a label or page-prefix that marks something as a runbook/SOP.

- PII redaction. Should we redact customer phone numbers / full email addresses / aadhaar / etc. before sending content to Claude? Default off; can be on per-customer (e.g. Reliance only).

- Auto-apply threshold for field corrections in Phase 3. Always require human approval, or auto-apply above a confidence threshold like 95%? Recommend always-approval for the first 2 weeks of Phase 3, then re-decide.

# 10. What's done already

Phase 0 is complete. Concrete artefacts in your project folder:

- docs/architecture.docx — the full system design.

- docs/dashboard_mockup.html — the UI design for the per-ticket agent view.

- docs/agent_view_report.html — same shape, populated with 10 real BetterPlace tickets analysed by Claude. Now includes the suggested-reply demo for #593721 and #593760.

- docs/ai_analysis_report.html — the cross-cutting findings from the same 10 tickets.

- data/zd_pull_output.json — the raw Zendesk pull (10 tickets + comments + 106 field defs).

- data/ticket_repository.json — the structured AI repository, seeded with all 10 tickets and their AI insights. This is what the Phase 1 system replaces with a live database.

- data/kb_drafts/593795_color_code_format.md — sample auto-drafted Confluence page for the color-code issue. Shape every future KB draft will follow.

- scripts/zd_pull.py — the working pull script, virtualenv-aware, .env-driven.

— End of plan —